## Table 1 (2)
OHPL Recovery Schedule (as of 15- Jul- 25) | [8 empty] | 13 July 25 | 20 July 25 | 27 July 25 | 3 Aug 25 | 10 Aug 25 | 17 Aug 25 | 24 Aug 25 | 31 Aug 25 | 7 Sep 25 | 14 Sep 25 | 21 Sep 25 | 28 Sep 25 | 05 Oct 25 | 12 Oct 25 | 19 Oct 25 | 26 Oct 25 | 02 Nov 25 | 09 Nov 25 | 16 Nov 25 | 23 Nov 25 | 30 Nov 25 | 07 Dec 25 | 14 Dec 25 | 21 Dec 25 | 28 Dec 25 | 04 Jan 25 | 11 Jan 25 | 18 Jan 25 | 25 Jan 25 | 01 Feb 25 | 08 Feb 25 | 15 Feb 25 | 22 Feb 25 | 1 Mar 25 | 8 Mar 25 | 15 Mar 25 | 22 Mar 25 | 29 Mar 25 | 05 Apr 25
[9 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
Sr. | Activity | Unit | Total | Actual | remaining | ENPPI's Proposal | SUC Response | Remarks
1 | Auguring (complete scope) | E | 172 | 125 | 47 | 2025-08-18 | 2025-08-31 | Consider external permit receive on time in 6 days a week
2 | Concrete Pouring 1st Stage ( Excavated) | E | 128 | 115 | 13 | 2025-08-05 | 2025-08-15
3 | Installation of pole bottom segment | E | 128 | 68 | 60 | 2025-08-05 | 2025-08-31 | Delivery will be July 30, 2025
4 | Concrete Pouring 2nd Stage | E | 128 | 59 | 69 | 2025-08-28 | 2025-09-25 | Delivery will be July 30, 2025 | bar: 17 to 20
5 | Installation of pole top segment | E | 128 | 0 |  | 2025-09-28 | 2025-10-15 | Delivery will be July 30, 2025 | bar: 17 to 23
6 | Concrete Pouring 1st Stage ( Aramco Permit ) | E | 44 | 0 |  | 2025-08-25 | 2025-09-30 | Consider external permit receive on time in 6 days a week | bar: 17 to 21
7 | Installation of pole bottom segment ( Aramco Permit ) | E | 44 | 0 |  | 2025-09-06 | 2025-10-25 | Consider external permit receive on time in 6 days a week | bar: 17 to 24
8 | Concrete Pouring 2nd Stage ( Aramco Permit ) | E | 44 | 0 |  | 2025-09-20 | 2025-11-06 | Consider external permit receive on time in 6 days a week | bar: 17 to 26
9 | Installation of pole top segment ( Aramco Permit ) | E | 44 | 0 |  | 2025-09-25 | 2025-11-21 | Consider external permit receive on time in 6 days a week | bar: 17 to 28
10 | Guy Anchor Excavation | E | 84 | 31 | 53 | 2025-08-15 | 2025-09-25 | Consider external permit receive on time in 6 days a week | bar: 17 to 20
11 | Guy Anchor Pouring (installation) | E | 84 |  |  | 2025-09-01 | 2025-10-25 | Consider external permit receive on time in 6 days a week | bar: 17 to 24
12 | Stringing - Accessories Installation and Stringing | m | 11326 | 0 |  | 2025-10-21 | 2026-01-20 | Consider external permit receive on time in 6 days a week | bar: 17 to 37
13 | HDD Crossing ( Railway ) | E | 1 | 0 |  | 2025-08-14 | 2025-08-25 | Consider external permit receive on time in 6 days a week
14 | HDD Crossing ( Highway ) Permits | E | 1 | 0 |  | 2025-08-29 | 2025-09-15 | bar: 17 to 19
15 | HDD Crossing ( Highway ) | E | 1 | 0 |  | 2025-09-09 | 2025-10-30 | Consider external permit receive on time in 6 days a week and MOT permit received on time (15 September 2025). | bar: 17 to 25
16 | Underground Crossings excavation | E | 14 | 0 |  | 2025-09-21 | 2026-01-15 | VO to be finalized to procure the materials on time (Maximum before 24 July 2025) and delivery of cable on December 15, 2025. | bar: 17 to 36
17 | Underground Crossings Cable laying | E | 14 | 0 |  | 2025-10-14 | 2026-02-14 | VO to be finalized to procure the materials on time (Maximum before 24 July 2025) and delivery of cable on December 15, 2025. | bar: 17 to 40
18 | Optimization Scope | LOT | 1 | 0 |  | - | 2026-03-06 | VO to be finalized to procure the materials on time (Maximum before 24 July 2025) and delivery of cable on December 15, 2025. | bar: 17 to 43
19 | Pre-commissioning and commissioning activities | LOT |  | 0 |  | 2025-11-20 | 2026-03-11 | VO to be finalized to procure the materials on time (Maximum before 24 July 2025) and delivery of cable on December 15, 2025. | bar: 17 to 44
20 | Punch Items Clearance | LOT |  | 0 |  | 2025-12-01 | 2026-03-31 | bar: 17 to 47
| ENPPI | SUC
# | Premises | Response
1 | Delivery of Last batch of steel poles at site on 20 July 25 | Energya still not submitted the Coating and Galvanization Report, Delivery will be July 30, 2025
2 | Mobilizing HDD contractor on ( permit revalidated till 30-Aug) | Mobilization will be after confirmation of MOT original scope will be covered in SAR HDD activities, 21 July 2025. HDD KoM with SA, ENPPI and HDD Subcontractor.
3 | - | Consider external permit receive on time in 6 days a week and MOT permit received on time (15 September 2025).
4 | - | VO to be finalized to procure the materials on time (Maximum before 24 July 2025).
Formulas:
SUC Response = [SUC Response, row above]+25